## Bug Tracking List
No. | Date | Status | Device | F/W | App | 發生率 | 重要性 | Issue Describtion | New Describtion | Mantis No. | Owner | Comment | Smart phone info
1 | 2024-11-15 | open | EW-7689FBE | 暫無 | Android_ v1.0.0.20241111 | 100% | S2 | 按左下箭頭,手機回到桌面,APP處於背景模式->再點選APP會要求輸入密碼. (其他背景模式不會要求輸入密碼) |  |  | charles | AP home page 無前一頁了,所以back鍵是關APP | Galaxy A34 / Android14
3 | 2024-11-15 | open | EW-7689FBE | 暫無 | Android_ v1.0.0.20241111 | 100% | S1 | 開啟生物辨識 -> 登出再登入後,生物辨識會回到關閉模式. |  |  | charles | 登出之後無法再登入,因此清除生物辨識,生物辨識spec應該要重新開始 | Galaxy A34 / Android14
18 | 2024-11-15 | open | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S1 | App Settings -> System Notification / Alert開啟儲存後,再登入查看是關閉狀態. |  |  | Cindy | 20241118 無依據 API name可實作 | iphone 11 / 16.0.2
19 | 2024-11-15 | open | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | 250407_ES2_v0.0.6.0402{15 Pro Max(18.3.2) & 16 Pro(18.0.1)}實測3次，1次差、2次好，v1.0.0.20250407{A34(14)}實測2次，1次差、1次好，懷疑可能是2.4G/5G問題。 Speed test出來的數據過低,同時間/網路測試出來只有Android的 3分之1. |  |  | Cindy | iOS 16,iOS 17差異 (The MASQUE Protocol) mobile 飛航模式 測試WiFi | iphone 11 / 16.0.2
28 | 2025-03-05 | open | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.0227 | 100% | S1 |  |  |  | Cindy | 20250305 說明 1. get{"event":"DevSiteGetTPSummary"} 每3秒 , 總共 60秒 (根據 SSID , VLAN 統計 API) 2. get{"event":"UpdateClientList"} 每3秒 , 總共 60秒 (根據 Device 統計 API) 3. 手動下拉 refresh 更新 1,2 | iphone 16 pro / 18.0.1
29 | 2025-03-05 | open | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.0227 | 3次 | S1 | Remove device後，再次Provision時，會有機率性會失敗。 |  |  | Cindy | 20250305 說明 提供 失敗log 給 fw 20250307 說明 fw : reboot 有機率性 driver initial failed 影響 Provisioning , Update, Factory Reset ,Remove 的功能" 20250408 ES2 fw v0.0.41 fixed | iphone 16 pro / 18.0.1
41 | 2025-03-07 | open | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.0307 | 20% | S2 | Provision時，選擇固定IP，完成後進入至Home Page，進入Device Status Page，Device會有機率被改成DHCP。 |  |  | Cindy | 20250307 說明 回報 fw 20250313 說明 fw : 1. TI: updating the dhcp/固定IP config to our database 2. Becker : SetConf 回雲端方能正確 20250408 ES2 fw v0.0.41 fixed | iphone 16 pro / 18.0.1
43 | 2025-03-07 | open | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250307 iOS_ v0.0.5.0307 | 100% | S2 | 使用admin權限帳號刪除Operator帳號後，使用Operator登入，出現"User ~!@#&^&^(* has been deleted"，建議將"~!@#&^&^(*"字串移除。 |  |  | Cindy | 20250310 說明 API 回應字串 字串移除/替換 : 請提供遵守規則 20250310 v0.0.5.0310 新增DataFormat檢查 參考Acelink Go -Data Format 網址 : https://docs.google.com/spreadsheets/d/1W1DrWZVMsWWggX-EEhPuMZVWd-DAtM56su848Mi117I/edit?gid=0#gid=0 | iphone 16 pro / 18.0.1
47 | 2025-03-05 | open | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S2 | Provision時，Network Registration選擇StaticIP，IP Info畫面顯示異常。 |  |  | Charles | 3/11 fix | Galaxy A34 / Android14
48 | 2025-03-05 | open | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S1 | Provision時，Network Registration選擇StaticIP，完成後，device不是被設定為固定IP。 |  |  | Charles | 20250307 說明 回報 fw ,fw 0.0.28 fix | Galaxy A34 / Android14
57 | 2025-03-06 | open | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 | 100% | S1 | v1.0.0.20250307實測_問題一樣。 Provision完成後，名稱都會是Model-L，不是一開始設定的名稱。 |  |  | Charles | 3/7 fix | Galaxy A34 / Android14
64 | 2025-03-06 | open | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 iOS_ v0.0.5.0303 | 100% | S1 | 250407_ES2_v0.0.6.0402{15 Pro Max(18.3.2)} & v1.0.0.20250407{A34(14)}實測，iOS顯示VLAN Setting(1)字串，Android顯示VLAN Setting(1000)字串。 Network Configuration Page，iOS顯示VLAN Setting字串，Android顯示management VLAN(1000)字串，請統一。 |  |  | Charles | 3/12 fix 20250408 Cindy : iOS APP , 依據UUID_VLAN 20250409 charles:fixed | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
66 | 2025-03-07 | open | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 iOS_ v0.0.5.0303 | 4次 | S1 | 1.Remove device、重開機到一半，發現Console卡住，無法開機，重啟後正常。+1 2.從Console Upgrade f/w後，重開機到一半，發現Console卡住，無法開機，重啟後正常。 3.從Console factory default後，重開機到一半，發現Console卡住IPQ5335命令列下，無法開機，重啟後正常。 |  |  | Cindy | 20250307 說明 fw : reboot 有機率性 driver initial failed 影響 Provisioning , Update, Factory Reset ,Remove 的功能 20250403 Cindy 測試provisioning ES2 版子 + fw v0.0.39 + v0.0.6.0403 測試 Remove device 6 次 OK | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
67 | 2025-03-07 | open | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250307 iOS_ v0.0.5.0307 | 1次 | S2 | Device Status Page，按下Update完成後並重開機，Console確認Device有更新成功，但已經被Deactived。 |  |  | Cindy | 20250307 說明 fw : reboot 有機率性 driver initial failed 影響 Provisioning , Update, Factory Reset ,Remove 的功能 | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
68 | 2025-03-07 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250307 iOS_ v0.0.5.0307 | 100% | S2 | 250409_ES2_v0.0.6.0408{16 Pro (18.0.1)} & v1.0.0.20250408{A34(14)}測試，iOS回到Device Status Page，Android回到Device List Page。 Device Status Page，按下Update後，iOS停在當下畫面，Android回到上一頁，請統一。 |  |  | Cindy | 20250310 fix 參考 Android作法 | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
71 | 2025-04-07 | open | EW-7689FBE | v0.0.39 ES2 | iOS_ v0.0.6.0402 | 100% | S1 | Provision時、Scan QR Code後，can not connect Device SSID，無法進行Provision流程。 |  |  | Cindy | 20250407 iphone 16 pro 回報 fw | iphone 16 pro / 18.0.1
72 | 2025-04-07 | open | EW-7689FBE | v0.0.39 ES2 | Android_ v1.0.0.20250407 | 100% | S1 | Provision時、Scan QR Code後，連接Device SSID後顯示已連線，但實際並未連上該Device SSID，無法進行Provision流程。 |  |  | Charles | 4/14 fixed,need wait 5G SSID ready | Galaxy A34 / Android14
73 | 2025-04-07 | open | EW-7689FBE | v0.0.39 ES2 | iOS_ v0.0.6.0402 | 100% | S2 | Provision完成後進入至Home Page，Online Device & Online Client都顯示0，須進入Device List Page後再返回才會顯示。 |  |  | Cindy | 20250407 建議 Home Page 手動 refresh 幾次 DevSiteGetTPSummary => 假資料 修改Provisioning: APP(v0.0.6.0407) + 10 秒跳回主頁 DHCP : 測試3次 reload_time 30 跳回主頁 0 （2／3） refresh 幾次後有數值 Static ip : 測試3次 reload_time:98 跳回主頁 數值正常 | iphone 15 pro max / 18.3.2
78 | 2025-04-07 | open | EW-7689FBE | v0.0.39 ES2 | iOS_ v0.0.6.0402 Android_ v1.0.0.20250407 | 70%🡅 | S1 | 假如有A Phone連接Device SSID，B Phone開啟App login至Home Page，A Phone會有很高的機率會斷開Device SSID。 |  |  | Cindy | 20250408 回報 fw Becker , 提供log | iphone 15 pro max / 18.3.2 Galaxy A34 / Android14
79 | 2025-04-08 | open | EW-7689FBE | v0.0.39 ES2 | iOS_ v0.0.6.0402 | 30%🡅 | S1 | App操作或long-run一段時間後，Device會Offline，發生問題時間不一。 |  |  | Cindy | 20250408 回報 fw Becker , 提供log | iphone 15 pro max / 18.3.2 Galaxy A34 / Android14
81 | 2025-04-08 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0402 | 100% | S1 | Wireless Frequency Settings內的Settings Channel Width Page，2.4GHz、5GHz & 6GHz修改後按下Save，使用WifiInfoView掃描後發現都沒有變更。 |  |  | Cindy | 20250408 剛剛與fw TI 確認後 目前功能還沒上 (應該/可能) 有機會於 1. WiFi profile (iphone 16 pro) ok 2. 本週客戶討論後 修改channel width 顯示: APP(v0.0.6.0408) | iphone 16 pro / 18.0.1
82 | 2025-04-08 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0408 Android_ v1.0.0.20250408 | 100% | S1 | Encryption Configuration Page設定WPA2+WPA3後按下Save，使用WifiInfoView掃描後發現安全性顯示為空白、無法辨識。 |  |  | Cindy | 20250408 回報 fw Becker & Alan | iphone 16 pro / 18.0.1
83 | 2025-04-09 | open | EW-7689FBE | v0.0.41 ES2 | Android_ v1.0.0.20250408 | 100% | S1 | Wireless Frequency Settings內的Settings Channel Width Page，2.4GHz、5GHz & 6GHz的item讀取不到，也無法點選修改。 |  |  |  |  | Galaxy A34 / Android14
84 | 2025-04-09 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0408 Android_ v1.0.0.20250408 | 100% | S2 | Usage Time Configuration Page，開關開啟並設定起始 ~ 結束時間後按下Save，只有等待到結束時間到達，無線網路才會關閉。 |  |  | Cindy | 20250410 回報 fw Becker & Alan | iphone 16 pro / 18.0.1 Galaxy A34 / Android14
85 | 2025-04-09 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0408 Android_ v1.0.0.20250408 | 100% | S1 | Usage Time Configuration Page，開關開啟並設定起始 ~ 結束時間後按下Save，將Device重啟後，等待到結束時間到達，無線網路也不會關閉。 |  |  | Cindy | 20250410 回報 fw Becker & Alan | iphone 16 pro / 18.0.1 Galaxy A34 / Android14
86 | 2025-04-09 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0408 Android_ v1.0.0.20250408 | 100% | S3 | Usage Time Configuration Page，開關開啟並設定起始 ~ 結束時間後按下Save，不論當天的開關是開啟或關閉，等待到結束時間到達，無線網路也會關閉，不會有影響。 |  |  | Cindy | 20250410 回報 fw Becker & Alan | iphone 16 pro / 18.0.1 Galaxy A34 / Android14
87 | 2025-04-09 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0408 Android_ v1.0.0.20250408 | 100% | S3 | 執行Provision流程時、於Device List Page，iOS & Android兩邊新增Device的按鈕位置不一致，建議統一。 |  |  | Cindy | 20250410 說明 Device = 0 => “Add" 顯示於頁面下方 , 右上方無 Device >= 1 => “Add" 顯示於頁面右上方無 | iphone 16 pro / 18.0.1 Galaxy A34 / Android14
88 | 2025-04-09 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0408 Android_ v1.0.0.20250408 | 100% | S1 | 執行Provision流程時、點選Site後，iOS & Android兩邊看到Info沒有Match。 |  |  | Cindy | 4/10 android fixed 20250410 說明 iOS 顯示 SSID , 無VLAN | iphone 16 pro / 18.0.1 Galaxy A34 / Android14
89 | 2025-04-09 | open | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0408 Android_ v1.0.0.20250408 | 100% | S2 | 承上題，於該頁面，iOS描述為Network Registration Page，Android描述為Network Selection Page，建議統一。 |  |  | Cindy | 4/10 android fixed 20250410 說明 0409 Demo後 , 客戶提供對應字串 | iphone 16 pro / 18.0.1 Galaxy A34 / Android14
PA_1 | 2025-05-29 | open | EW-7689FBE | v0.2.05 ES2 | IOS V0.2.31.0528 | 100% | S2 | 登入頁面輸入帳號及密碼的顯示字體太小 ，輸入的字體也是太小，不易辨識，建議至少跟 首頁內 Speed Test 字體一樣大。更友善使用者。 |  |  | Cindy | 20250603 v0.2.35 fixed | iphone 16 / 18.4
PA_2 | 2025-05-29 | open | EW-7689FBE | v0.2.05 ES2 | IOS V0.2.31.0528 | 100% | S3 | 掃描QR Code 後，停留在掃描QR頁，不知再等啥， 建議 提示狀態，例: 處理中。 |  |  | Cindy |  | iphone 16 / 18.4
Closed：2025/4/9
6 | 2024-11-15 | close | EW-7689FBE | 暫無 | Android_ v1.0.0.20241111 | 100% | S2 | 250312_RD有跟客戶確是是否要加 “記憶密碼功能”, 客戶拒絕 每次開啟APP都要重新輸入密碼,建議新增記憶帳密功能. |  |  | charles | 客戶未開這spec | Galaxy A34 / Android14
10 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | 250312_RD有跟客戶確是是否要加 “記憶密碼功能”, 客戶拒絕 每次開啟APP都要重新輸入帳密,建議新增記憶帳密功能. |  |  | Cindy | 啟用生物辨識 視為 記住帳密 | iphone 11 / 16.0.2
20 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 50% | S2 | 250312_RD告知用樹梅派模擬的, 之後都會用Furuno AP , 所以可以拿掉了 Add Device -> 配對成功後,沒有出現配對成功訊息.(機率50%) |  |  | Cindy | 20241118 iOS : 模擬裝置 The network connection was lost. Task <AC30C592-7017-4058-A925-88881F37FEF1>.<1> failed strict content length check - expected: 415, received: 2, received (uncompressed): 0 Task <AC30C592-7017-4058-A925-88881F37FEF1>.<1> finished with error [-1005] Error Domain=NSURLErrorDomain Code=-1005 "The network connection was lost." UserInfo={NSLocalizedDescription=The network connection was lost., NSErrorFailingURLStringKey=http://192.168.8.5/cgi2/param.cgi?action=list&group=Network.Cloud, NSErrorFailingURLKey=http://192.168.8.5/cgi2/param.cgi?action=list&group=Network.Cloud, _NSURLErrorRelatedURLSessionTaskErrorKey=( "LocalDataTask <AC30C592-7017-4058-A925-88881F37FEF1>.<1>" ), _NSURLErrorFailingURLSessionTaskErrorKey=LocalDataTask <AC30C592-7017-4058-A925-88881F37FEF1>.<1>, NSUnderlyingError=0x3020bd590 {Error Domain=kCFErrorDomainCFNetwork Code=-1005 "(null)" UserInfo={NSErrorPeerAddressKey=<CFData 0x300faf980 [0x1f02bbeb0]>{length = 16, capacity = 16, bytes = 0x10020050c0a808050000000000000000}}}} The network connection was lost. 20241119 iOS : 模擬裝置 上電超過 12小時 , 回應不完整JSON Object ,fixed方式 模擬裝置 重新上電 , 回應完整JSON Object: http://192.168.8.5/cgi2/param.cgi?action=list&group=Network.Cloud Successfully decoded: { "Network": { "Cloud": { "Enable": true, "DeviceID": "670311AE292EA6426224482BA30F81A3C4E65C194EE44F6BF2F87EDC53C53A6E", "Provisioned": false, "APIURL": "", "DDNSURL": "", "OAuth2URL": "", "UploadURL": "", "DDNSURL": "", "OAuth2URL": "", "UploadURL": "", "Status": "Offline", "StoragePlan": 1, "SyncSetting": "NoSync" } } } http://192.168.8.5/cgi2/param.cgi?action=list&group=Network.Cloud Successfully decoded: { "Network": { "Cloud": { "Enable": true, "DeviceID": "670311AE292EA6426224482BA30F81A3C4E65C194EE44F6BF2F87EDC53C53A6E", "Provisioned": true, "APIURL": "", "DDNSURL": "", "OAuth2URL": "", "UploadURL": "", 2024-11-19 10:34:11.863186+0800 Neton[653:51291] [] __nwlog_err_simulate_crash simulate crash already simulated "-[nw_ip_channel_inbox initWithPath:flow:parameters:delegate:] flow (929AB327-6147-461B-BCEB-4D64202C9E93, interface: utun4, viable, assigned) does not specify local endpoint" | iphone 11 / 16.0.2
42 | 2025-03-07 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.0307 | 100% | S2 | Provision時，選擇固定IP並跑完流程後，將Device重開機，Device就變回DHCP。 |  |  | Cindy | 20250307 說明 回報 fw 20250313 說明 fw : 1. TI: updating the dhcp/固定IP config to our database 2. Becker : SetConf 回雲端方能正確 20250408 ES2 fw v0.0.41 fixed | iphone 16 pro / 18.0.1
62 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 iOS_ v0.0.5.0227 | 100% | S1 | v1.0.0.20250307實測，看是iOS新增字串"MAC："，還是Android移除字串"MAC："。 因v1.0.0.20250306_按+後無回應，此issue無法確認。 Blocklist Setting Page，iOS & Android顯示方式不match，請統一。 |  |  | Charles Cindy | 3/5 fix 20250310 iOS fix 參考 Android作法 | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
69 | 2025-03-07 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250307 iOS_ v0.0.5.0307 | 100% | S1 | Site Selection Page，無法刪除重複的Site。 |  |  | Charles | 此為DashBoad設定共用service導致底下site無法被刪除,Furuno 應無使用Dashboard功能,spec請找cloud 確認 | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
70 | 2025-03-07 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.0307 | 100% | S2 | Site Selection Page，新增不同名稱的Site，也無法刪除。 |  |  | Cindy | 20250307 fix Refresh 問題 , 參考Android作法 | iphone 16 pro / 18.0.1
74 | 2025-04-07 | close | EW-7689FBE | v0.0.39 ES2 | iOS_ v0.0.6.0402 | 100% | S2 | 點選Client List Page，畫面一直顯示●●●●●跑馬燈。 |  |  | Cindy | 20250407 請問有無實際 Client 裝置連接 AP ? Client List => 真實數據 , 已回報 fw 不穩定 | iphone 15 pro max / 18.3.2
75 | 2025-04-07 | close | EW-7689FBE | v0.0.39 ES2 | iOS_ v0.0.6.0402 Android_ v1.0.0.20250407 | 100% | S2 | App login，Android會記住Mail，iOS不會，請統一。 |  |  | charles | 4/7 fixed | iphone 15 pro max / 18.3.2 Galaxy A34 / Android14
76 | 2025-04-07 | close | EW-7689FBE | v0.0.39 ES2 | Android_ v1.0.0.20250407 | 100% | S1 | 點選Client List Page，畫面無任何顯示。 |  |  | charles | 4/8 fixed | Galaxy A34 / Android14
77 | 2025-04-07 | close | EW-7689FBE | v0.0.39 ES2 | Android_ v1.0.0.20250407 | 100% | S1 | 承上題，返回Home Page、再點選Client List Page，畫面會一直轉圈圈，無法返回，只能刷退App。 |  |  | charles | 4/8 fixed | Galaxy A34 / Android14
80 | 2025-04-08 | close | EW-7689FBE | v0.0.41 ES2 | iOS_ v0.0.6.0402 | 100% | S1 | Wireless Frequency Settings內的Band Setting Page，點選MLO Network or 6GHz任一選項，按下Save後，使用WifiInfoView都掃描不到6GHz的SSID。 |  |  | Cindy | 20250408 與fw Becker確認並使用 WifiInfoView : 1. 6GHz + WPA3 2. MLO Network + WPA3 change Encryption 法規 : 2.4G 15秒 , 5G 60秒 | iphone 16 pro / 18.0.1
Closed：2025/3/7
2 | 2024-11-15 | close | EW-7689FBE | 暫無 | Android_ v1.0.0.20241111 | 100% | S2 | Forgot Password-> 輸入完 Mail,鍵盤無法下拉收起,擋住 Reset button,無法繼續下一步. |  |  | charles | 11/22 fixed | Galaxy A34 / Android14
4 | 2024-11-15 | close | EW-7689FBE | 暫無 | Android_ v1.0.0.20241111 | 100% | S1 | Network 頁面目前無內容. |  |  | charles | 2nd 階段job | Galaxy A34 / Android14
5 | 2024-11-15 | close | EW-7689FBE | 暫無 | Android_ v1.0.0.20241111 | 100% | S2 | 230306_v1.0.0.20250306_問題一樣。 可重複創相同名稱的 Site,建議防呆. |  |  | charles | 11/19 fixed | Galaxy A34 / Android14
7 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | Confirm password 的明碼無效.(眼睛按鈕) |  |  | Cindy | fixed | iphone 11 / 16.0.2
8 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | 註冊帳號還沒將確認信啟動,此時登入APP沒有出現提示訊息.(ex:請將確認信啟動) (Android有做) |  |  | Cindy | fixed(20241113新增Alert) | iphone 11 / 16.0.2
9 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | 可重複創相同名稱的 Site,建議防呆. |  |  | Cindy | fixed | iphone 11 / 16.0.2
11 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | Add Site頁面 -> 沒有回上一頁功能.(強迫新增 Site) (Android有做) |  |  | Cindy | NavigationStack 即可back fixed(新增 back icon) | iphone 11 / 16.0.2
12 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | Add Site頁面 -> 下方沒有顯示已存在的 Site. (Android有做) |  |  | Cindy | fixed | iphone 11 / 16.0.2
13 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | Forgot Password->Pin code輸入錯誤沒有提示訊息. |  |  | Cindy | fixed(20241113新增Alert) | iphone 11 / 16.0.2
14 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | Forgot Password->Pin code輸入錯誤,要重新輸入APP鍵盤出現速度很慢,甚至鍵盤出不來. |  |  | Cindy | fixed iphone UI | iphone 11 / 16.0.2
15 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | Surname/Name 欄位可輸入,但變更失敗. |  |  | Cindy | fixed(UserSet ->UserGet ) | iphone 11 / 16.0.2
16 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S1 | 生物辨識->設定臉部生物辨識,開啟APP會馬上閃退.(Recover:重新安裝APP) |  |  | Cindy | fixed iphone permission | iphone 11 / 16.0.2
17 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S1 | APP linitalization -> 按了會閃退. |  |  | Cindy | fixed SecItem Delete callback | iphone 11 / 16.0.2
21 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S2 | Remove Device -> 沒有刪除成功的訊息,裝置依然顯示在清單內.(裝置實際已刪除) |  |  | Cindy | fixed (DevDel->DevList,DevSiteUpdateClientList) | iphone 11 / 16.0.2
22 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S1 | Operator登入後,依然可編輯 User Managerment. |  |  | Cindy | 20241113 之前對應 AppNew 異常 , 關閉對應實作 fixed | iphone 11 / 16.0.2
23 | 2024-11-15 | close | EW-7689FBE | 暫無 | IOS_ v0.0.5 | 100% | S1 | admin權限無法刪除 Operator. |  |  | Cindy | 20241113 之前對應 AppNew 異常 , 關閉對應實作 fixed | iphone 11 / 16.0.2
24 | 2025-03-04 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% |  | Provision時，手機跟device若不在同一網段，Scan完QR Code按Next後，會停在當下，無法繼續下一步，建議彈出警告訊息。 |  |  | Cindy | 20250307 fix 新增警告訊息視窗 | iphone 16 pro / 18.0.1
25 | 2025-03-04 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | Provision時，點選StaticIP，輸入完 IP Info 後按Next，會delay 1 ~ 2 秒才會執行下一步。 |  |  | Cindy | 20250305 fix 檢查 Invalid IP Address 新增 Loading View , 防呆. | iphone 16 pro / 18.0.1
26 | 2025-03-04 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | 承上題，當下按Next無反應時，再次按下Next，當執行完程序，會一直重複彈出Home Page，建議防呆。 |  |  | Cindy | 20250305 fix 檢查 Invalid IP Address 新增 Loading View , 防呆. | iphone 16 pro / 18.0.1
27 | 2025-03-04 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | 承上題，這時在Home Page，Online Device數量偵測不到，須點選Online Device登入後才能偵測。 |  |  | Cindy | 20250305 說明 get{"event":"DevSiteGetTPSummary"} 每3秒 , 總共 60秒 (根據 SSID , VLAN 統計 API) | iphone 16 pro / 18.0.1
30 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | Device Status Page，Download/Upload顯示1xxx M....。 |  |  | Cindy | 20250305 fix | iphone 16 pro / 18.0.1
31 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | Device Setting內的IP Address Settings Page，輸入完 IP Info 後按Confirm，會delay約 4 秒才會執行，建議防呆。 |  |  | Cindy | 20250305 fix 檢查 Invalid IP Address 新增 Loading View , 防呆. | iphone 16 pro / 18.0.1
32 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S1 | Client List Page，點選BlockList Setting，App就閃退。 |  |  | Cindy | 20250305 fix 1. 檢查 name base64 Encode 防呆. 預設 name : "DefaultName" 2. BlockList Add 檢查 Mac 規則 | iphone 16 pro / 18.0.1
33 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | Network Configuration Page，Publishing the network開啟(關閉)後按下Save，再次開啟(關閉)並按下Save會無回應，須再次開啟(關閉)後按下Save才有回應。 |  |  | Cindy | 20250305 fix 修正暫存變數 | iphone 16 pro / 18.0.1
34 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | Network Configuration Page，Guest network開啟(關閉)後按下Save，再次開啟(關閉)並按下Save會無回應，須再次開啟(關閉)後按下Save才有回應。 |  |  | Cindy | 20250305 fix 修正暫存變數 | iphone 16 pro / 18.0.1
35 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S1 | Wireless Frequency Settings內的Settings Channel Width Page，點選6GHz任何一項，App就閃退。 |  |  | Cindy | 20250306 fix 修正暫存變數 | iphone 16 pro / 18.0.1
36 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250227 | 100% | S2 | Device Status Page，點選Update，字串顯示Would you like to update to 0.0.01？，但實際執行後，從Console log看到的版本是v0.0.23。 |  |  | Cindy | 20250306 fix 讀取 model_ui | iphone 16 pro / 18.0.1
37 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250306 | 100% | S1 | Wireless Frequency Settings內的Settings Channel Width Page，6GHz點選任一選項，按下Save後，都會回到160MHz。 |  |  | Cindy | 20250306 fix | iphone 16 pro / 18.0.1
38 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250306 | 100% | S2 | Provision完成後，回到Home Page，此時畫面往右滑，會在回到上一個設定步驟頁面。 |  |  | Cindy | 20250306 fix 修正 path 路徑 | iphone 16 pro / 18.0.1
39 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250306 | 100% | S2 | 承上題，這時重新設定一組新的IP，Provision完成後進入至Home Page，Online Device數量就會偵測不到。 有時會直接卡在設定步驟頁面。 |  |  | Cindy | 20250306 fix 修正 path 路徑 | iphone 16 pro / 18.0.1
40 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | iOS_ v0.0.5.20250306 | 25% | S2 | Provision完成後進入至Home Page，Online Device數量會有機率性偵測不到。 |  |  | Cindy | 20250306 fix 修正更新的讀取變數 | iphone 16 pro / 18.0.1
44 | 2025-03-04 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 30%🡅 | S2 | Provision時，Scan完QR Code，輸入device name後，device name的欄位會留在當下畫面(欄位內容被清空)。 |  |  | Charles | 3/5 fix | Galaxy A34 / Android14
45 | 2025-03-04 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S2 | 承上題，QR Code程序完成後，來到Network Registration，再次device name欄位，輸入不同名稱後按Yes，然後按下DONE，完成Registered設定，回到Device List Page，名稱會是一開始設定的名稱，不是後來設定的名稱。 |  |  | Charles | 3/5 fix | Galaxy A34 / Android14
46 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S1 | v1.0.0.20250306_Device List Page問題一樣。 Device List Page，device Info顯示異常；Client List Page也是。 |  |  | Charles | 3/6 fix 3/5 update,please check again | Galaxy A34 / Android14
49 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S2 | 進入Device List Page，沒有get{"event":"UpdateClientList"}，但有Get{"event":"DeviceDeactived"}。 |  |  |  |  | Galaxy A34 / Android14
50 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S2 | Factory Rest後，回到Home Page，Online Device數量還是顯示為1。 |  |  | Charles | 3/5 fix | Galaxy A34 / Android14
51 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S2 | v1.0.0.20250306_問題一樣。 Networking Setting Page，關閉(開啟)SSID A並按下Save後，再次開啟(關閉)SSID A並按下Save會無回應，須退回上一頁再進入此頁，修改後按下Save才有回應。 |  |  | Charles | 3/5 fix | Galaxy A34 / Android14
52 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 100% | S1 | Client Detial Page，做過一次Block / Unblock後，就再也無法使用此功能。 |  |  | Charles | 3/5 fix | Galaxy A34 / Android14
53 | 2025-03-05 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 | 30%🡅 | S1 | v1.0.0.20250306_按+後無回應。 Blocklist Setting Page，按+後，輸入Client Name & MAC後，按下Block後機率性無法新增。 |  |  | Charles | 3/5 fix,length=12 | Galaxy A34 / Android14
54 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 | 30%🡅 | S2 | Network Configuration Page，右上方的Save鍵不好按，建議修改。 |  |  | Charles | 3/6 fix | Galaxy A34 / Android14
55 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 | 100% | S2 | Device Status Page，點選Update，字串顯示Would you like to update to null(應顯示版號)？，請修正。 |  |  | Charles | 3/6 fix | Galaxy A34 / Android14
56 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 | 100% | S2 | Device List & Client List Page的設定都只是畫面閃一下，建議參考其它Page，修改設定能有提示或是告知訊息。 |  |  | Charles | 3/7 fix | Galaxy A34 / Android14
58 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 | 100% | S2 | 此版修正容易造成右上方的按鈕不好按。 |  |  | Charles | 3/6 fix | Galaxy A34 / Android14
59 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 | 100% | S2 | Add Site頁面 -> 下方沒有顯示已存在的Site。 |  |  | Charles | 3/7 fix | Galaxy A34 / Android14
60 | 2025-03-07 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250307 | 100% | S1 | 可重複創相同名稱的Site，建議防呆。 |  |  | Charles | 3/7 fix | Galaxy A34 / Android14
61 | 2025-03-04 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250303 iOS_ v0.0.5.20250227 | 100% | S2 | Provision完成後，iOS回到Home Page，Android回到Device List Page，請統一。 |  |  | Charles | 3/5 fix | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
63 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 iOS_ v0.0.5.20250227 | 100% | S2 | Publishing the network、Wireless Frequency Settings & Encryption Configuration設定後，Conssole log搜尋關鍵字找不到，看不出有無變化。 |  |  | Cindy | 20250306 說明 Publishing the network : AP_SSID Wireless Frequency Settings : AP_SSID , AP_Radio Encryption Configuration : AP_SSID | Galaxy A34 / Android14 iphone 16 pro / 18.0.1
65 | 2025-03-06 | close | EW-7689FBE | v0.0.22 | Android_ v1.0.0.20250306 iOS_ v0.0.5.20250303 | 100% | S1 | Device Status Page，按下Update後，Console有收到UpdateFirware的Event，但實際上沒有更新成功。 |  |  | Cindy | 20250306 說明 fw : ## Error: "difw" not defined all of dut's bootloader must be upgraded to "U-Boot 2016.01 (Feb 12 2025 - 11:32:04 +0800)" to support fw ugprade via cloud | Galaxy A34 / Android14 iphone 16 pro / 18.0.1

## Change History
iOS_App
Date | Version | Release Note
2024-11-15 | v0.0.5.1108 | first release.
2025-02-27 | v0.0.5.0227 | phase 2 release
2025-04-02 | v0.0.6.0402 | phase 2 release (ES2)
Android_App
Date | Version | Release Note
2024-11-15 | v1.0.0.20241111 | 1.Furuno neton 1st 階段. 2.Android 只支援13以上.
2025-03-03 | v1.1.0.0303 | 1.Furuno neton 2nd 階段 2.UAT5
2025-04-07 | v1.1.0.0407 | 1.usage format update 2.lan port cpnfig

## PA2 Test Report
ID | Category | Feature item | Description>ExpectedResult | DUT version | iOS App version | iOS Result | DUT version | Android App version | Android Result | Status | Comment
|  |  | the latest version: | 0.3.01 | 0.3.04 |  |  |  | Google | AP FW
1 | Login
2025-01-01 |  | Create Account | Tap “Register Now“ to create an account. You will receive an email for account verification. Click the link in the mail for account verification. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0209d0604 | PASS
2025-01-02 |  | APP Login | Use the registered account and password to log in APP. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0209d0604 | PASS
2025-01-03 |  | Forgot Password | Tap “Forgot Password”. Input your email and press the "Reset" button. You will receive a time-limited (10 minutes) with a 6-digit code in the email. Then reset your password. Go back to the "Log in" page and log in with your new password. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0209d0604 | PASS
2 | First time only
2025-02-01 |  | Let’s Start With | Please check the "Let’s Start With" page when using the app for the first time. Tap "Next" button. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0209d0604 | PASS
2025-02-02 |  | Site Registration | Add a new Site. Then Save. Select an existing Site. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0209d0604 | PASS
2025-02-03 |  | Network Registration or Network Selection | Add a Network. (WiFi or VLAN). Then Save. Select an existing Network. Then Next. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0209d0604 | PASS |  | iOS 顯示 Network Registration Android 顯示 Network Selection
2025-02-04 |  | Device Registration | Scan QR code. Input a Device name, then press OK. If success, the message will pop up. “The device has been registered.” Configure IP Address Setting for the device. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0209d0604 | PASS |  | 新註冊帳號後，認證後，從 APP UI -> NEXT後，進入掃描連結QRCODE，會一直無法找到裝置(確定網路是通的)。離開APP GUI，再進入 APP UI 後，回到Menu畫面，發現沒有Device online. 並且再點擊進入Dvice Registration，還是無法加入Network. Tina PS: 要default的SSID 才能夠device registration. Chris: iOS APP 在add device, 設定完 DHCP/VLAN按下 "Next" 後，會等一段長時間，建議在動畫上，或給個小提示，讓user 知道大約要等多久
3 | Home
2025-03-01 |  | Menu(top-left) | Tap the “Menu” icon in the top-left corner. >Make sure you can open and close the "Menu" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Related ID: 11
2025-03-02 |  | Alert(top-right) | Tap the “Alert” icon in the top-right corner. >Make sure you can open and exit the "Alert" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Related ID: 5
2025-03-03 |  | Site Selection | Tap the “Site” icon on the "Home" page. >Make sure you can open and exit the "Site Selection" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Related ID: 3-12~3-15
2025-03-04 |  | Network Selection | Tap the “Network” icon on the Home page. >Make sure you can open and exit the "Network Selection" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Related ID: 3-16~3-22
2025-03-05 |  | Download/Upload | Check the "Download" and "Upload". >Make sure they can display the WiFi traffic statistics of the device. >Make sure they can update after "Reflash". | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Reflash動作，請參考 ID 3-10 Note: 目前只測一台device Tina: Client後，主頁面往下滑reflash 後並沒有任何變動，維持相同數值，並沒有立即update。
2025-03-06 |  | Online Device | Display the current number of online devices. >Make sure it can update after "Reflash". | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Reflash動作，請參考 ID 3-10
2025-03-07 |  | Online Client | Display the current number of online Wi-Fi clients. >Make sure it can update after "Reflash". | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | note:目前只測一台device + 1 client
2025-03-08 |  | Speed Test | Tap the “Speed Test” icon on the "Home" page. >Make sure you can open and exit the "Speed Test" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Related ID: 12
2025-03-09 |  | Self Diagnostics | Tap the “Self Diagnostics” icon on the "Home" page. >Make sure you can open and exit the "Self Diagnostics" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Related ID: 12 Tina: DNS 和 Internet 顯示的內容一樣，秀出的資訊應該要有所不同。
2025-03-10 |  | Reflash | Tap and hold the center of the screen, then pull down until you see the animation. Once it appears, release your finger to refresh the data. >Please ensure the refresh function is working correctly. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
2025-03-11 |  | Check the 4 icons at the bottom. (Home/Network/Report/Settings) | Tap the “Network” icon at the "Home" page's bottom. Tap the “Report” icon at the "Home" page's bottom Tap the “Settings” icon at the "Home" page's bottom >Make sure you can open Network/Report/Settings page and go back to the Home page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
2025-03-12 |  | Site Selection -page | Tap the “Site” icon near the top center of the "Home" page to open the "Site Selection" page. >Check the display, there must be "Current Site" and "Available" parts. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
2025-03-13 |  | Site Selection -Add | Tap the icon in the top-right corner. Then tap the "Add" button. >Make sure you can add a new site. >The new site will appear under "Current Site". | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
2025-03-14 |  | Site Selection -Delete | Tap the icon in the top-right corner. Then tap the "Delete" button. >Make sure you can delete an existing site. >Make sure the removed site disappeared from the list. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: Remove site 有防呆禁止刪除current site. (至少要留一個Site)
2025-03-15 |  | Site Selection -switch site | Switch to SiteB from SiteA. Tap a site from the "Available" list. Yes or Cancel. Tap "Yes" to change. >Make sure the Current Site displays SiteB >Back to the "Home" page, and check the Online Device and Online Client. They must meet the SiteB's info. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
2025-03-16 |  | Network Selection -page | Tap the “Network” icon near the top center of the "Home" page to open the "Network Selection" page. >Check the display, there must be "Current Network" and "Available" parts. >Tap an available network(ex: Network A), then go back to the "Home" page. >Tap the "Network" at the bottom, and make sure the configuration belongs to Network A. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Note: 據RD描述，此為檢視 Network 功能(SSID 設定)， 若要看AP 吃了多少wifi config, 要看Home>Online Device>select one>Edit icon>Network Setting Tina:收到。
2025-03-17 |  | Network Selection -Add-WiFi | Tap the icon in the top-right corner. Then tap the "Add" button Select "WiFi" and input SSID and password, then Save. >Make sure the created Network(WiFi) appears in the "Available" list. >Home>Online Device>select one>Edit icon>Network Setting, make sure the created Network was configured into the online device(s). | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
2025-03-18 |  | Network Selection -Add-VLAN | Tap the icon in the top-right corner. Then tap the "Add" button Select "VLAN" and input a VLAN(name) and a VLAN number, then Save. >Make sure the created Network(VLAN) appears in the "Available" list. >Home>Online Device>select one>Edit icon>VLAN Setting, make sure the created Network(VLAN) can be used for configuring E1 port. | 0.3.00 | 0.3.00 | PASS |  |  | TBD | Fixed | 20250609 點選 WiFi 更換成 VLAN , APP 截圖如右所示. 20250610 新增 VLAN 屬於APP <---API--->雲端 , 不影響現有/新增 ＡP
2025-03-19 |  | Network Selection -Remove-WiFi | Tap the icon in the top-right corner. Then tap the "Remove" button Select one "WiFI Network" from the "Registered Network" list. Then tap "Remove. >Check OK message. >Make sure the selected "WiFi Network" disappears from the "Available" list. >Home>Online Device>select one>Edit icon>Network Setting, make sure the selected Network was removed from the online device. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: Edit 能修改SSID成功。
2025-03-20 |  | Network Selection -Remove-WiFi -At least one | If "Network (WiFi)" is the only available network, it cannot be removed. Attempting to remove it should trigger a warning. >It must pops up a warning. | 0.2.10 | 0.2.41.0612 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: Add 能新增SSID成功。無法刪除currenr SSID的警告有跳出。
2025-03-21 |  | Network Selection -Remove-VLAN | Prerequisites: This VLAN configuration must not be used for WiFi and E1~E5 ports. Tap the icon in the top-right corner. Then tap the "Remove" button Select one VLAN Network from the "Registered Network" list. Then tap "Remove. >Check OK message. >Make sure the selected VLAN Network disappears from the "Available" list. >Home>Online Device>select one>Edit icon>VLAN Setting> "+ "icon, make sure the VLAN was removed from "Select the Registered Network list". | 0.3.00 | 0.3.00 | PASS |  |  | TBD | Fixed | Acelink GO JSON https://docs.google.com/spreadsheets/d/1SqLFX4veNd366kmdTwTsK5TpADc9_Zz142KQAY8Nfqc/edit?gid=606530463#gid=606530463 | 有兩個Network (VLAN) 無法刪除 Aaaaaaaa99(99) VvvvVan1000(1000) 可用PA 測試帳號登入查詢 chrischeng@edimax.com.tw 12345678 | 20250613 雲端 fixed 請再測試一次
2025-03-22 |  | Network Selection -Share Network | Tap the icon in the top-right corner. Then tap the "Share Network" button. Select one WiFi Network from the "Registered Network" list. Then tap "Share Network". >Check the QR code/SSID/Password info.(should be the current Network) Tap the "Sharing" button. >Make sure it can jump to the iOS/Android Sharing Menu. Use another phone to scan this QR code. >Make sure that can configure the Wi-Fi connection. | 0.2.17 | 0.2.42.0613 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Note:Sharing button只驗証 跳轉到手機的"分享選單" Tina: 安卓系統跳出QRCODE後，我用另一台Client手機掃QROCDE，可連結該WIFI 並正常連線上網。 20250609 fixed 請更新安裝連結 iOS APP version 0.2.39.0609
4 | Network Status
2025-04-01 |  | Device List | Tap the “Online Device” to enter the “Device List” page. >Make sure you can open and exit the "Device List" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | 細部檢查在 第6章
2025-04-02 |  | Client List | Tap the “Online Client” to enter the “Client List” page. >Make sure you can open and exit the "Client List" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | 細部檢查在 第8章 Note: 只顯示目前Network-WiFi(SSID)下的 client 數量 Tina: Client已斷線，但還是有show 之前的資訊在Client Details，沒有立刻更新狀態。
2025-04-03 |  | Navigation Bar | Check 4 icons(Home/Network/Report/Settings) at the bottom. >Enter Network/Report/Settings, you can tap the “Home” icon to go back to the "Home" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
5 | Alert
5-1 |  | Alert | There are 3 types of alert. Red: Error ; Yellow: Warning ; Green: Information Not ready. |  |  | TBD |  |  | TBD |  | Not ready Furuno_APP_UI_SPEC : Alert List : 目前無法完成對應客戶的Alert Table Message check, pls refer to this link https://docs.google.com/spreadsheets/d/1ltseRcVQV4xTvpQtcfTBD64BnmMm9qG0ybMHizzuDNg/edit?gid=84841052#gid=84841052
5-2 |  | Upgrade FW | If there is a new firmware version on the server, it must have a notification in the Alert list. "Firmware has been uploaded." + "the new firmware version number" Tap this notification. Tap the "Update now". >Make sure the connected devices can be upgraded to the new firmware. | 0.3.01 | 0.3.01 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Chris: 測過 0.3.00 upgrade to 0.3.01 Chris: iOS App 點了 "Update now" 之後，沒有任何反饋動畫或訊息，user 會不曉得 device 正在更新中 Tina: Alert -> Update now -> 從console看能看到正在FW upgrade，並且reboot device-> check FW : v0.2.11 (ps: 會update後會發現Device of off line)
5-3 |  | Client Details | Not ready. Tap a new device. Jump into the “Client Details” page. ?? | 0.3.00 | 0.3.00 | FAIL |  |  | TBD | Retest | Tina: 顯示 Client 類別(TV, Phone, …) : APP default icon: Phone 。(我用Wifi Client 圖示還是顯示 dafult的Phone)。 手機(i phone 15) 連上的話，會顯示"Random MAC"。 20250623 Becker--Please disable "Random MAC" in your iPhone's settings 20250708 Chris: 0.3.00>當手機(取消random MAC)連上後，等了五分鐘後，Alert 裡依舊沒有該手機的相關訊息
6 | Device List
6-1 |  | Device List -Device info | Tap the “Online Device” to enter the "Device List" page. >Make sure each device has these info items. >Online/Offline: It must display the current status properly. >Upload/Download: It must display the upload/download traffic. >Online Client: It must display the number of Wi-Fi clients properly. | 0.3.00 | 0.3.00 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | FAIL | Retest | 20250609 AP 回應 Radio ( 5G ) 有誤 , 20250602已回報 fw. APP 變更為讀取 SSID , 請更新安裝連結 iOS APP version 0.2.38.0606 20250610 1台AP，1台MacBook Pro連接 1個 SSID , 數量顯示 2 (2.4G , 5G 且 IP 相同) note: Online Client 數量是隨著 Network selection(SSID) 而變化 目前issue: 一台手機連上，數量會顯示2 (2.4G , 5G 且 IP 相同) 20250623 Becker--the results was from WiFi Driver so we won't change its behavior at this moment WiFi command to check : wlanconfig athx list sta
6-1-1 |  | Device List -Device info (Online) | Keep one device active. Home page: reflash. Enter the "Device List" page. >The "Device List" must display this device as "Online." | 0.2.17 | 0.2.42.0613 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
6-1-2 |  | Device List -Device info (Offline) | Power off the device. Wait for 300 seconds. Home page: reflash. Enter the "Device List" page. >The "Device List" must display this device as "Offline". | 0.2.19 | 0.2.44.0618 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | note: 需等300秒 20250618 雲端 /v2/DevGetInfo fw AP -- 超過 300 秒 --- > 雲端 (websocket ping pong) DUT 狀態 : online --- >offline
6-2 |  | Device List -Add | Tap the “Online Device” to enter the "Device List" page. Tap the top-right icon. It will pop up the “Add” and “Remove” buttons. Tap the "Add" button to add a new device to the Device List. [Add>Let’s Start With>Next>select a Registered Site>select a Registered Network>Next>Scan QR code>input a device name>OK>IP Address Setting>Next>wait for a few minutes] >Make sure this device can be configured with "Network configuration". >App: The "Home" page must include this device. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: 當已成功加入第一台Device後，(Site registration: sqa , test)當已成功加入第一台Device後(如: sqa)， 當我想註冊另一個site(test)，Network Selection->NEXT-> 進入Read the QR code on the device itself，卻一直無法註冊成功。
6-3 |  | Device List -Remove | Tap the "Remove" button. [Remove>select a Registered Device>Remove or Cancel] Tap the “Remove” button, then the list will not display the device. >App: The "Home" page must NOT include this device. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
6-4 |  | Device Status -Check | Tap “Online Device”>Device List>select a Device>Device Status Check these items on the "Device Status" page. >Edit icon (into Device Setting page) >Online/Off line >IP >Version >E1~E5 (T: VLAN tagged) >Download/Upload (Wi-Fi) >Online Clients (Can be flushed: Tap and hold the Online Clients table screen, then pull down.) | 0.3.00 | 0.3.00 | PASS |  |  | TBD | Fixed
6-5 |  | Device Status -Update | Tap the top-right icon on the "Device Status" page. Tap the “Update” button. Display the latest version and the current version. Click the “Update” button to upgrade the AP firmware. Yes or Cancel. Tap "Yes" to start the upgrade process. >Make sure this device can upgrade to the latest firmware version. >App: The "Home" page can reflash this device's info. (Download/Upload/Online Client) >App: Go to this page and check the current firmware version again. | 0.2.24 | 0.2.50.0630 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | note: fw upgrade功能 ; cmd: cat /etc/fw_version Tina : 0.2.10->0.2.11 ，從console 可看Device version Chris: 建議跳個警告訊息，因為update 過程中，從APP端完成看不出需要等待多久
6-6 |  | Device Status -Restart | Tap the top-right icon. Tap the “Restart”. OK or Cancel. Tap "OK" to reboot this device. >Make sure this device can reboot. >App: The "Home" page can reflash this device's info. (Download/Upload/Online Client) | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: 從console 能看出reboot device.
6-7 |  | Device Status -Factory Reset | Tap the top-right icon. Tap the “Factory Reset”. Read the "Factory Reset" page. Tap the "Factory Reset" button at the bottom. Yes or Cancel. Tap "Yes". This device will be removed from the "Device List". >This device will be reset to factory default. >App: Home page>Online Device will not include this device. >Home>Online Device>Device List will remove this device. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
7 | Device Setting
7-1 |  | Device Setting -Model -Serial No -Version | Online Device>Device List>select a Device>Device Status Tap the "Edit" icon to enter the "Device Setting" page. Check this device info: Model / Serial No / Version. >Model must be "SW-730" >Serial No, test version displays 12345678 >Version must be the current version. | 0.2.17 | 0.2.42.0613 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
7-2-1 |  | Device Setting -IP Address Setting -DHCP | Tap "IP Address Setting" to enter the "IP Address Setting" page. Change it to DHCP. >Make sure this device can be configured to the DHCP client. >Make sure this device can get the IP from the DHCP server. | 0.2.17 | 0.2.42.0613 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: 可從Client端確認是否能成功修改ip address...(static ip) 但是...ip改變之後，Device會offline.
7-2-2 |  | Device Setting -IP Address Setting -Static IP | Change it to Statics IP. >Make sure this device can be configured to a fixed IP. | 0.2.17 | 0.2.42.0613 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
7-2-3 |  | Device Setting -IP Address Setting -VLAN | Not ready. 1. 目前無法更改 2. 此功能測試，有疑慮 | 0.3.01 | 0.3.01 | FAIL |  |  | TBD | Fixed | Refer to VLAN pre-test Test Case 6 20250708 Chris: 0.3.00 如果把 IP Address Setting, DHCP 改綁 VLAN400, 會無法save ，它會跳回 ManagementVLAN(1) 20250711 Chris: 0.3.01，br0 會掛掉，重啟後可以恢復
7-3 |  | Device Setting -VLAN Setting | Change VLAN settings for E1~E5. >E1~E5 can be configured VLAN | 0.3.00 | 0.3.00 | PASS |  |  | TBD | Fixed
7-4 |  | Device Setting -PoE Setting | Spec request. This item must grey out. | 0.3.00 | 0.3.00 | PASS |  |  | TBD | please remove this | 20250609 依據 客戶 20250321回信 Please grey it out in AP. android:客戶要求AP grey it out,已完成AP部分
7-5-1 |  | Device Setting -Network Setting -enable SSID | Tap the "Network Setting" to enter the "Network Setting" page. Switch multiple Network settings to ON and Save. >Make sure the device can be configured with multiple SSIDs. | 0.2.17 | 0.2.42.0613 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: 可從Client端確認該SSID是否被關閉， iwconfig也可以查詢。 20260616 fw v0.2.17 fixed disable_SSID 數目錯誤問題 20250613 回報 fw APP : 1 site 4 ssid disable_SSID 數目 : 1 , 主頁 /v2/DevSiteGetTPSummary 得到 enable SSID 數目 : 2 fw v0.2.15 1. disable_SSID : 測試 3 次 , 100%重現 , 生效SSID + 80秒 (1) disable_SSID : [] , 測試API /v2/DevSiteGetTPSummary , /v2/DevSiteGetClientList 正常 (2) disable_SSID : ["UUID_SSID1"] , 測試API /v2/DevSiteGetTPSummary array_of_SSID 剩下 2 ssid
7-5-2 |  | Device Setting -Network Setting -disable SSID | Switch multiple Network settings to OFF and Save. >Make sure the device can turn off the select Network(SSID). | 0.2.17 | 0.2.42.0613 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | iOS: app 動畫有點久 Tina: disable後SAVE之後, reload有點久(大約快1分鐘)
7-5-3 |  | Device Setting -Network Setting -disable all | Switch all Network settings to OFF and Save. >It should pop up a msg. “At least one network is to keep settings.” | 0.2.17 | 0.2.42.0613 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
8 | Client List
8-1 |  | List | Not ready. Tap “Online Client” to enter the "Client List" page. Check each client's icon/Download/Upload/Signal. >Make sure the icon displays properly. (TV, Phone…; Currently the default category icon is Phone.) >Make sure Download/Upload can display properly. >Make sure the Wi-Fi signal can display the client's signal strength. | 0.3.01 | 0.3.01 | TBD |  |  | TBD | Retest | 目前 client 圖示皆為"phone" 20250609 default : "phone" icon 20250610 fw 新版 提供 os 值 ( 部分封包可解析作為 pattern , 若遇到無法異常回報 fw) Tina: 0.2.11 用手機或wifi client連，圖示一樣顯示"phone" icon 20250623 Becker--Cindy please show "Windows", "iPhone", "iPAD", "MacOS" if possbile Becker--what's the TV device tested by PA???? > Sony TV X85K Command to enable debug messages in order to get the OS type for new device's patthern: echo 7 > /proc/sys/kernel/printk echo echo dsc_debug on > /proc/dsc/dsc_config 20250710 Chris: 0.3.01 使用iPhone/Win11 NB/TV: Sony TV X85K, icon 皆是 phone
8-2-1 |  | Client Detail | Not ready. Select a client to enter the "Client Detail" page. Check this client signal/icon/name/download/upload/Access Point/IP/MAC. >Make sure the signal strength displays properly. >Make sure the icon displays properly. (TV, Phone…; Currently the default category icon is Phone.) >Make sure the Download/Upload can disply properly. >Make sure the Access Point display is correct and check which AP the client is connected to. >Make sure the IP display is correct and check the client's IP. >Make sure the MAC display is correct and check the client's MAC. |  |  | FAIL |  |  | FAIL | Retest | iOS: 有時候 Home>Oline Client數量正常，但點進去Client List 卻顯示為空的，必需重新登入APP才會正常 20250625 charles:Android部份下拉reflash對Client 有>10以上存在問題,客戶也未提供如何reflash資訊 20250609 (1) Client List 下拉更新API回應資料 & filter by SSID(主頁) (2) 可能是時間差 Home> Oline Client => API /v2/TPSummary 回應 Client List => API /v2/DevSiteUpdateClientList , /v2/DevSiteGetClientList 回應 Tina: 安卓系統與IOS狀況相同。下拉reflash感覺沒作用。 20250623 Becker--Cindy please show "Windows", "iPhone", "iPAD", "MacOS" if possbile Becker--what's the TV device tested by PA???? > Sony TV X85K,
8-2-2 |  |  | 建立多個SSID Network Selecion ，選SSID#4 NoteBook 連上SSID#4 Online Client>Client List 選一個wireless client，然後就APP 就跳掉了 | 0.3.01 | 0.3.01 | FAIL |  |  |  |  | 20250714 fixed iOS v0.3.04f0301d0714
8-3 |  | Block | Tap the “Block” button to block the client’s traffic. >The client icon will change to the “Stop” icon. >The client must be not able to access the Internet. >"Unblock" appears at the bottom. | 0.3.01 | 0.3.01 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | FAIL | Fixed | 20250708 Chris: iOS: 0.3.00 用兩台手機(皆關閉 random mac)連上，block一台，一開始可以 block，但該手機重新連線，就又可以通了 問題: 功能不完整，client list 會變成三個 client(block狀態)，按 Unblock 會有 error android:Blocl後client似乎不售引響 Tina: 不能 Block，將已連線上的Client，點選block,從client端還是能ping到device
8-4 |  | Unblock | Tap the "Unblock" button to allow the client's traffic. >The client icon will change to a normal icon. >The client must be able to access the Internet. >"Block" appears at the bottom. | 0.3.01 | 0.3.01 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | FAIL | Fixed | iOS: 有機率 會出現 error msg: set metadata SSID_ACL: Row not exist. 按"<" 回上頁時，"BlockList Setting" 按鈕依舊存在 Tina: v0.2.11: 安卓因不能 Block client，所以我無法驗證Unblock功能。 20250610 fixed 請更新安裝連結 iOS APP version 0.2.40.0610 20250714 註: unblock 後，需要等一段時間，wifi client 要重新連線
8-5 |  | BlockList Setting -page | Tap the top-right icon on the "Client List" page. Tap the "BlockList Setting" to enter the "BlockList" Setting" page. >Make sure you can open and exit the "BlockList Setting" page. >If there is any client in this list, check the client's info and MAC address. | 0.2.19 | 0.2.44.0618 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | FAIL |  | android:06/25 fix Tina: v0.2.11: 確認進入"BlockList Setting" ，出現亂碼。 20250610 fixed 請更新安裝連結 iOS APP version 0.2.40.0610
8-6 |  | BlockList Setting -ADD | Tap the top-right icon on the "BlockList Setting" page. Tap the "Add" button. >Input Client Name and MAC Address. >Make sure the client's traffic can be blocked. | 0.3.01 | 0.3.01 | FAIL | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | FAIL | Fixed | 20250714 Chris: iOS: 手動加入NoteBook的MAC(已經有取消隨機MAC設定), 依舊不能block，它會block 一小段時間，但沒過多久它有通了 Tina: v0.2.11: 安卓 不能 Block client.
8-7 |  | BlockList Setting -Remove | Tap the top-right icon on the "BlockList Setting" page. Tap the "Remove" button to enter the "MAC Access Control List" page. Select one client, then tap "Remove". >Make sure the client's traffic can recover. | 0.2.17 | 0.2.42.0613 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: v0.2.11: 安卓 可以remove item. Chris: iOS 可移除，等block功能修正後，該項要補驗
9 | Network Configuration
9-1 |  | Check "Network Configuration" page | Tap the “Network” icon at the bottom. Check the "Network Configuration" page. >Make sure you can open and exit the "Network Configuration" page. >This page should have these items. Change SSID Change Password Publishing the network Guest Network Wireless Frequency Settings Encryption Configuration VLAN Setting QoS Setting Traffic Configuration Usage time Configuration Save button at the top-right corner | 0.2.19 | 0.2.44.0618 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
9-2 |  | Network Configuration -Change SSID | Tap the "Change SSID" and change the SSID. >Make sure the new SSID can configured into the device. >Make sure the STA can connect with this SSID and access the Internet. | 0.2.19 | 0.2.44.0618 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | Tina: 修改SSID後，Device 會變off line.. ( RD 需要做後續處理，回到iwconfig 可以查到SSID已被改變，但device被強制off line_ Chris: deive 變 offline 的問題，已修正(DUT v0.2.19+app 0.2.44)
9-3 |  | Network Configuration -Change Password | Tap the "Change Password" and change the password. >Make sure the new password can configured into the device. >Make sure the STA can connect with this SSID and access the Internet. | 0.2.19 | 0.2.44.0618 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
9-4 |  | Network Configuration -Publishing the network | Tap the "Publishing the network" and change it to disable/enable. >Make sure the SSID stops broadcasting. >Make sure the SSID starts broadcasting. | 0.3.00 | 0.3.00 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | NA | Fixed | 20250708 Chris: 0.3.00 fixed. note: 需等待個幾分鐘 Tina: disable或enable,是掃得到，也可以連上線
9-5 |  | Network Configuration -Guest Network | Tap the "Guest Network" and change it to enable. >Make sure the STA can connect it. >The STA must go to the portal page first. >The STA cannot access the LAN devices. | 0.3.00 | 0.3.00 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS | Retest | 目前行為: STA 可連上該SSID，但 ip/subnet 為自定義，無法和LAN 相通，portal page 按下OK，才可上網 Guest Network 只能指定一個SSID 20250624 - EmilyLiao 請問您是在PC上測試嗎? 有pop up 視窗要求使用者登入嗎? 20250708 Win PC 會跳 portal page, 但 iphone 不行
9-5-1 |  | Network Configuration -Guest Network -Check all items | Check these items of Guest Network settings. -Logo (下一版 要能上傳 最大 1M bytes) -Custom Message -Timeout Setting (注意，STA 從 AP1 跳到 AP2，時間會重新計算，不會累加，已知問題，客戶已知) -Redirect to Website | 0.3.00 | 0.3.00 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | Tina：東西有存在。 Tina: Guest Networl 一開，device ?
9-5-2 |  | Network Configuration -Guest Network -Change it to another SSID | Home>Network Selection, select SSID#2 Network>Guest Network, enable SSID#2 >The SSID#1 will not be the Guest Network. >Use the STA to connect SSID#1. (Not Guest Network) >Use the STA to connect SSID#2. (Guest Network) | 0.2.19 | 0.2.44.0618 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
9-6-1 |  | Network Configuration -Wireless Frequency Settings -Band | Tap "Wireless Frequency Settings" and select a "Band" option. Verify that each setting functions as expected: >Default: Ensure the STA can connect to both 2.4GHz and 5GHz. >MLO: Ensure the STA can connect to 2.4GHz, 5GHz, and 6GHz. (WPA3 only) >2.4GHz Only: Ensure the STA can connect only to 2.4GHz. >5GHz Only: Ensure the STA can connect only to 5GHz. >6GHz Only: Ensure the STA can connect only to 6GHz. (WPA3 only) | 0.3.01 | 0.3.04 | PASS | 0.2.19 | NetOn_DV0.0.0.f0214d0613 | FAIL | Fixed | note: ath0~15為2G ; ath16~31為5G ; ath32~ issue: 當加密為WPA2，切換到 6G only 有問題，必須把加密改成 WPA3 only 才會通 20250620 : iOS v0.2.46.0620 fixed iOS 安裝連結如下: https://edimax-iotapp.github.io/Neton/iOS/UAT5/Neton_UAT5.html 說明 : 6G only + WPA3 only 6G only + None(OWE) MLO + WPA3 only MLO + None 方法 : WPA2 -> 設定 Band 頁面 6G only 反灰不可選 (Becker) 6G only -> 設定加密頁面 WPA2 only , WPA2/WPA3 反灰不可選 參考文件 : https://docs.google.com/spreadsheets/d/1Hfp-jawqOGozj2znNCCLPZyFrqjkNPQVIgnyS6OyLgA/edit?gid=0#gid=0 Tina: Band Setting-> 2.4GHz Only -> Save->用iwconfig看wifi內容，還是能看到5GHz。 (其他設定也依樣沒作用) 20250623-Becker Changed in FW v0.2.20 Changed WPA type form 0 (none) to OWE (13) for 6G open security
9-6-2 |  | Network Configuration -Wireless Frequency Settings -Channel width | Not ready. Tap the "Wireless Frequency Settings" and modify "Channel width". | 0.2.19 | 0.2.44.0618 | FAIL | 0.2.19 | NetOn_DV0.0.0.f0214d0613 | FAIL | Emily Fixing | Tina: 將5GHz 改成40MHz or 20MHz , save. Client 連上5G後， wlanconfig 柴連線狀況，還是維持default 的160MHz. Tina comment: 請問RD是否能提供檢查當前DUT的bandwwidth or channel 之類訊息
9-6-3 |  | Network Configuration -Wireless Frequency Settings -Channel | 下一版會新增，到時再看設定選項怎麼安排 2.4G channel (Auto, ch1 ~ ch13) 5G channel: (Auto, ch?? 先依照目前能支援的channel) 6G channel: (Auto, ch?? 先依照目前能支援的channel)
9-7 |  | Network Configuration -Encryption Configuration | Tap "Encryption Configuration" and select a opton for encryption.. Verify that each setting functions as expected: >WPA2 only: Ensure the SAT can connect to the SSID.: >WPA2+WPA3: Ensure the STA can connect to the SSID. >WPA3 only(6G): Ensure the STA can connect to the SSID. >None: Ensure the STA can connect only to the SSID. ps: None for 6G is OWE | 0.2.19 | 0.2.44.0618 | TBD | 0.2.19 | NetOn_DV0.0.0.f0209d0604 | TBD | Fixed | Tina comment: 請問RD是否能提供檢查當前DUT的Encryption之類訊息? 因為我是把它改成未加密，但其他加密方式 我無法驗證。 PS: 6GHz 只能用WPA3來連線，看起來功能尚未完成。 20250620 WifiInfoView ( 桌機版 ) 20250625-Becker for 6G only and MLO, only WPA3 and Open (OWE) are available | 20250619 測試 fw v0.2.19 , APP iOS V0.2.44.0618 1. Factory Reset =＞ Default status 2. provisioning 可以完成 至 TPSummary 3. 短時間內 , 超過 300秒 無 websocket ping pong 4. Device offline 5. reboot 6. S23+ WiFi 列表 : 生效SSID 7. S23+ 連線生效SSID 失敗 8. S23+ WiFi 列表 : 無生效SSID 9. S23+ WiFi 列表 : 生效SSID 10. S23+ 連線生效SSID 成功 20250618 測試 fw v0.2.18 回報 設定 MLO 於 iPhone 16 Pro 無法連線生效SSID成功 測試 fw v0.2.19 回報 provisioning 後須 reboot , disable_SSID與生效SSID 數目方正確. 20250617 測試 fw v0.2.17 (1) disable_SSID 測試 ok (1 site , 5 ssid 任一變更 disable_SSID數目) 20250613 Guest Network : iOS APP version 0.2.42 測試 fw v0.2.15 (1) disable_SSID : [ ] (2) 測項 provisioning 後 : 1 site 4 ssid 且 創建 Guest Network , Client 端裝置可以透過 Guest Network 正常上網. (3) 關閉 (2) Guest Network , Client 端裝置可以透過 SSID 正常上網. 20250610 Guest Network : iOS APP version 0.2.40 測試 fw v0.2.11 (1) 測項 provisioning 前 : 1 site 2 ssid , 其中1 ssid 創建 Guest Network , provisioning 流程ok 且 Client 端裝置可以透過 Guest Network 正常上網. (2) 測項 provisioning 後 : 1 site 1 ssid 且 創建 Guest Network , Client 端裝置可以透過 Guest Network 正常上網.
9-8 |  | Network Configuration -VLAN Setting | Not ready. Tap the "VLAN Setting" and modify VLAN setting. | 0.2.19 | 0.2.44.0618 | TBD | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | TBD | Fixed
9-9 |  | Network Configuration -QoS Setting | Tap the "QoS Setting" and enable WMM. | 0.2.19 | 0.2.44.0618 | NT | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | NT | Fixed | 待檢查指令 20250623 Becker--Mike please check WMM
9-10-1 |  | Network Configuration -Traffic Configuration -Band Limitation | Spec?? Tap the "Traffic Configuration" and enable "Enable Traffic Control". Edit Band Limitation. >Overall bandwidth limit ?? >Device bandwidth limit ->fail | 0.2.19 | 0.2.44.0618 | NT | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | NT | Retest | 問題: Overall bandwidth limit 是指什麼? 定義為何? issue: device bandwidth limit 無效 20250623-Becker Current defines: Overall bandwidth limit is "1000Mbps" Please use charoit to do tests for bandwidth limit
9-10-2 |  | Network Configuration -Traffic Configuration -Application bandwidth limit | Spec?? Tap the "Traffic Configuration" and enable "Enable Traffic Control". Add a rule for application bandwidth limit. >Make sure the TCP/UDP traffic can meet the settings. | 0.2.19 | 0.2.44.0618 | NT |  |  | NT | Retest | 問題: 該限速是否包含LAN PC/ WiFi STA
9-11 |  | Network Configuration -Usage time Configuration | Tap the "Usage Time Configuration " and enable "Setting usage time". Edit the usage time. >Make sure the STA's usage time complies with the settings. | 0.2.19 | 0.2.44.0618 | FAIL | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | FAIL | Fixed | note: 該schedule設定會套用所有SSID，所以一個SSID啟動，其它SSID會一起生效 20250620 雲端 API 參數 : site id 如右附圖
10 | Settings
10-1 |  | Check "Settings" page | Tap the “Settings” icon at the bottom. >Make sure you can open and exit the "Settings" page. >This page should have these items. Licenses Management User Management Time Configuration LED Settings Update Configuration Reboot Configuration | - | 0.2.44.0618 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
10-2 |  | Licenses Management | Spec?? -Add License -Execution | - | 0.2.44.0618 | NA | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | NA | APP | 問題: 不清楚該功能有什麼作用? 1)不知如何 Add 2)執行 Excution 後，無回饋，具體功能什麼?
10-3 |  | User Management -Add (operactor account) | Tap the "User Management" to enter the "User Management" page. >Make sure you can open and exit the "User Management" page. Tap the top-right icon and tap Add to create an operator account. >Make sure you will receive a confirmation mail. >Make sure you can add an operator account. >The new operator account will appear in the list. | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | 20250610 Login : Register ( admin 權限) Home 右上側欄 : Account setting ( admin 權限) User Management : admin 權限者 新增/刪除/轉移權限 operator operator : 無顯示 User Management
10-4 |  | User Management -operator account login | Use the created operator account to log in the APP. >Make sure the operator account cannot see this "User Management" page. | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
10-5 |  | User Management -Heir User | Tap the top-right icon and tap "Heir". Select one account and tap "Done" to change the permissions. >Make sure the selected account changes to admin. >Make sure the App will go back to the Login page. >Make sure the selected account can see this "User Management" page. | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
10-6 |  | User Management -Delete (operactor account) | Use the admin account to log in. Tap the top-right icon and tap Delete to delete an operator account. >Make sure you can delete the operator account. >The operator account will disappear from the list. | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
10-7 |  | Time Configration | Tap the "Time Configuration" to enter the "Time Configuration" page. >Make sure you can open and exit the "Time Configuration" page. >Make sure it displays Tokyo time. >Make sure the device's time is the same time zone. | 0.2.11 | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | 20250609 顯示日本時間 APP(20250417) 創建 site , 背景自動設定日本時區API Chris: 0.2.11+iOS app v0.2.40 -> pass (東京時間)
10-8 |  | Led Settings | Spec?? Tap the "LED Settings to enter the "Led Settings" page. >Make sure you can open and exit the "Led Settings" page. >Make sure you can change and save the LED ON/OFF setting. >Make sure you can specify the "Lights out time" schedule. | 0.2.19 | 0.2.44.0618 | NA | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | NA | Retest | 功能不明，是定義 device LED on/off 跟 LED亮的時間嗎? 20240624-Becker Please check EPS for LED behavior
10-9 |  | Update Configuration -page | Tap the "Update Configuration" to enter the "Update Configuration" page. >Make sure you can open and exit the "Update Configuration" page. >Check the display version. It should show the current device firmware version. | 0.2.19 | 0.2.44.0618 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS |  | Tina: 下面有表示有新版本的資訊
10-10 |  | Update Configuration -Auto Update | Switch the "Auto Update" switch button. >Make sure it can be switched and saved. When the "Auto Update" is enabled. The Schedule must show the default. (08:00~20:00) Change the schedule. >Make sure the device's firmware can upgrade in the setting range. |  |  |  | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | FAIL | Fixed | Tina: 到時再看有沒有更新到新版???? ===> 目前沒看到會自動更新。
10-11 |  | Reboot Configuration -page | Tap the "Reboot Configuration" to enter the "Reboot Configuration" page. >Make sure you can open and exit the "Reboot Configuration" page. | 0.2.19 | 0.2.44.0618 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
10-12 |  | Reboot Configuration | Switch the "Automatic Reboot" switch button. >Make sure it can be switched and saved. When the "Automatic Reboot" is enabled, the Schedule must appear. Change the schedule. >Make sure the device will reboot at the set time. | 0.2.17 | 0.2.42.0613 | FAIL | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | NT | Fixed | note: App 只管設定時間，reboot 時間以DUT內的時間為主(東京時區) 20250617 APP 設定 Tue 14:30 , API 送出 Tue 14:30 - 15:00 => DUT Tue 14:30 - 15:00 執行 Reboot Chris: 時間一到 device 就一直一直重開 (問題可複現: 一台device, 三個SSID, 設定Rboot Configuration) (new Site 也是一樣有問題) 20250617 fw 已複製issue , 待新版
10-12-1 |  | Reboot Configuration -repeatable (next week) | Wait for next week. >Make sure the dvice will reboot at the same time. | 0.2.17 | 0.2.42.0613 | NT | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | NT | Fixed | 先不測，不確定是否可重複 reboot
11 | Menu
11-1 |  | Menu page | Tap the “Menu” icon in the top-left corner. >Make sure you can open and swipe left to exit the Menu page. >Check the display name, it should be Surname+Name. >This page should have these items. Logout Account Settings App Initialization Spport App Settings Guidance About the App | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS
11-2 |  | Logout | Tap the "Logout icon to log out. >Make sure it can go back to the Log-in page. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS
11-3 |  | Auto Logout -Timeout | Spec?? Don't close the App, wait for ?? minutes >Make sure the App can log out automatically. | - | 0.2.33.0602 | NT | - | NetOn_DV0.0.0.f0214d0613 | NT | APP | Chris: 請iOS/Android 開發人員明確指示出 timeout 時間，何時APP 會自動登出, 目前有看到 "Token expired: 訊息，當錯誤訊息出現，只能重開 app
11-4 |  | Account Settings -page | Tap the "Account Settings" icon to enter the "Account Settings" page. >Make sure you can open and exit the "Account Settings" page. >Check these items at below: >Surname (can be modified) >Name (can be modified) >Email (cannot be modified) >Change Password >Fingrerprint authentication login >Save button (in the top-right corner) | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS
11-5 |  | Account Settings -Surname/Name | Modify the "Surname" and "Name", then tap the "Save" button. Go back to the "Menu" page, and check the display name. >Make sure the display name is the modified Surname+Name. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS |  | 建議: iOS 按下save 後，要有一點回饋動作，不然user不知道是否更改成功 20250613 fixed 新增設定成功視窗 請更新安裝連結 iOS APP version 0.2.42.0613
11-6 |  | Account Settings -Change Password page | Tap the "Change Password" to enter the "Change Password" page. >Make sure you can open and exit the "Change Password" page. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS
11-7 |  | Account Settings -Change Password | Input the correct "Current password" and a new password. >Make sure it can jump to the "Login" page. >Make sure you can use the new password to log in. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS
11-8 |  | Account Settings -Change Password -Incorrect Current Password | Input the incorrect "Current password". >Make sure it can pop up a warning. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS |  | MSG: 目前顯示 Password not matched.
11-9 |  | Account Settings -Change Password -Same password | Spec? Input the correct "Current password" and a new password. The new password is the same as the current password. >Make sure it pops up a warning. | - | 0.2.33.0602 | NA | - | NetOn_DV0.0.0.f0214d0613 | NA | APP | 建議: 新舊密碼一樣時 ，沒有防呆，會跳至登入畫面 Tina: 建議同上。
11-10 |  | Account Settings -Change Password -Incorrect Confirm Password | Input the correct "Current password", then input a new password and a wrong confirm password. >Make sure it can pop up a warning. | - | 0.2.33.0602 | PASS | - | NetOn_DV0.0.0.f0214d0613 | PASS |  | MSG: 目前顯示 Password & Confirm Password do not match. Tina: MSG: 目前顯示 Password not matched.
11-11 |  | Account Settings -Fingerprint authentication login | Spec?? 驗証指紋/ Face ID (At first Phone should enable 驗証指紋/ Face ID ) >Click Account Settings >Click Finger authentication login ,then Enable >Done and Save. >logout APP >Check 驗証指紋/ Face ID cannot workable. | 0.2.17 | 0.2.42.0613 | FAIL | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | FAIL | APP | Tina: Fingerprint auth login Enable後，Click "Done",back to Account setting, save, 回到目錄，登出後。重新login 並未能使用指紋辨識，回到Finger auth login,還是disable. Chris(iOS): 應該是spec issue, 若手動登出後，該項功能又變回 Disable，無法再用指紋/face id 登入 android:Fingerprint auth login 是開APP auth login,登出後無效,故為disable,請使用back 關APP
11-12 |  | App Initialization | Tap “App Initialization” icon to enter the "App Initialization" page. >Make sure you can open and exit the "App Initialization" page. Tap "Initialization" button". >Email/Password will be cleared. >Fingerprint authentication login will change to OFF. >Make sure it jumps to the Loing page. | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | note: Menu>Account Settings>Fingerprint authentication login 要打開，就能刷臉/刷指紋
11-13 |  | App Settings -System Notification | 關閉的話，以下的三個選項，要反灰 打開的話，APP在手機上要推播，以及 email |  |  | TBD |  |  | TBD | Becker | TBD 中，目前無作用
11-14 |  | App Settings -Alert -Firmware Update -Report | -Alert -Firmware Update -Report <請參考右邊附圖> |  |  | TBD |  |  | TBD | Becker
11-15 |  | Support | Tap “Support” icon to enter the "Support" page. >Make sure you can open and exit the "Support" page. >Check the page content. (サポ─ト) | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | 20250609 依據 客戶 20250606回信已提供 , 請更新安裝連結 iOS APP version 0.2.38.0606 Tina: click下去沒反應。 android:V0.0.0.f0214d0613 fixed
11-16 |  | Guidance | Tap “Guidance” icon to enter the "Guidance" page. >Make sure you can open and exit the "Guidance" page. >Check the page content. (ガイド) | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | 20250609 依據 客戶 20250606回信已提供 , 請更新安裝連結 iOS APP version 0.2.38.0606 Tina: click下去沒反應。 android:V0.0.0.f0214d0613 fixed
11-17 |  | About the App -page | Tap “About the App” icon to enter the "About the App" page. >Make sure you can open and exit the "About the App" page. | - | 0.2.40.0610 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
11-18 |  | About the App -Version | Check the App version. >Make sure it displays the correct App version. | - | 0.2.40.0610 | PASS | 0.2.11 | NetOn_DV0.0.0.f0209d0604 | PASS
11-19 |  | About the App -Terms of Service | Tap "Terms of service". >Make sure you can open and exit the "Terms of Service" page. >Check the page content. (利用規約) | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | TBD | APP | -建議 Terms of Service 字串大小寫要統一 20250609 依據 客戶 20250606回信已提供 , 請更新安裝連結 iOS APP version 0.2.38.0606 Tina: 為什麼這三的頁面都一樣("Terms of service". ,"Privacy Policy"., "License" 內文都一樣?. android:V0.0.0.f0214d0613 fixed
11-20 |  | About the App -Privacy Policy | Tap "Privacy Policy". >Make sure you can open and exit the "Privacy Policy" page. >Check the page content. (プライバシ ─ポリシ─) | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | TBD | APP | -建議 Privacy Policy 字串大小寫要統一 20250609 依據 客戶 20250606回信已提供 , 請更新安裝連結 iOS APP version 0.2.38.0606 Tina: 為什麼這三的頁面都一樣("Terms of service". ,"Privacy Policy"., "License" 內文都一樣?. NetOn_DV0.0.0.f0214d0613: android:V0.0.0.f0214d0613 fixed
11-21 |  | About the App -License | Tap "License". >Make sure you can open and exit the "License" page. >Check the page content. (ライセンス) | - | 0.2.40.0610 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | TBD | APP | 20250609 依據 客戶 20250606回信已提供 , 請更新安裝連結 iOS APP version 0.2.38.0606 Tina: 為什麼這三的頁面都一樣("Terms of service". ,"Privacy Policy"., "License" 內文都一樣?. android:V0.0.0.f0214d0613 fixed
12 | Speed Test/Self Diagnostics
12-1 |  | Speed Test | Tap the “Speed Test” icon on the Home page. >Make sure you can open and exit the "Speed Test" page. Tap the "START" button to test the speed. >Make sure you're able to get the following data:Download/Ping/Upload. >Make sure you can do the Speed Test again. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | 註: 只能測你手機到Internet. 若要測device WiFi，記得切換手機上的SSID連線
12-2 |  | Self Diagnostics -page | Tap the “Self Diagnostics” icon on the Home page. >Make sure you can open and exit the "Self Diagnostics" page. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
12-3 |  | Self Diagnostics -normal test | Enviornment: Internet-Router-Device AP)) ((phone Prerequisites: AP and phone can access Internet. When you open this "Self Diagnostics" page, an animation will appear. >After the animation finish, check DHCP/DNS/Internet items. >Their status LED must be green. >Tap the "info" icons beside DHCP/DNS/Internet to show info. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
12-4 |  | Self Diagnostics -Re-diagnosis | Disconnect the Internet. (Plug Internet cable from the Router.) Tap this "Re-diagnoise" button. >Make sure Re-diagnoise button can work properly, >DNS and Internet status LED should be NG. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS | APP | iOS: 建議按下"Re-diagnoise" 最好小動畫再跑一次，不然使用者會不曉它有重新動作
12-5 |  | Self Diagnostics -abnormal test | Enviornment: Internet--x--Router-Device AP)) ((phone Prerequisites: AP and phone cannot access Internet. When you open this "Self Diagnostics" page, an animation will appear. >After the animation finish, check DHCP/DNS/Internet items. >DNS and Internet status LED should be NG. >Tap the "info" icons beside DHCP/DNS/Internet to show info. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | TBD |  | 如果要讓 DHCP 要變為NG 必須讓手機要不到IP，會變得很麻煩
13 | Report
13-1 |  | Report -page | Tap the “Report” icon at the bottom. >Make sure you can open and exit this "Report" page. >Check these items. Traffic chart Client list | 0.2.10 | 0.2.33.0602 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS
13-2 |  | Report -Traffic bar chart | Check the Traffic bar chart. | 0.2.10 | 0.2.33.0602 | PASS | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | PASS |  | 20250618 APP iOS v0.2.46.0620 更新 Report頁面 Y軸單位支援 GB,TB,PB顯示 20250618 APP iOS v0.2.44.0618 Report頁面的年度直方圖 : 當月 + 前 11個月 (AP_SSID , AP_VLAN) 20250610 APP iOS v0.2.39.0609 Report頁面新增 /v2/DevSiteGetThroughput 回應資料繪製直方圖 (AP_SSID)
13-3 |  | Report -Client list | Not ready. Check the Client list. | 0.2.10 | 0.2.33.0602 | TBD | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | TBD | Becker | Spec 尚未確定
13-4 |  | Report -Log Saving | Not ready. Tap the top-right icon in this Report page. Tap "Log Saving" button to enter "Log Saving" page. >Make sure you can open and exit the Log Saving page. >Make sure the Log Saving button can work properly. (spec ??) | 0.2.10 | 0.2.33.0602 | TBD | 0.2.17 | NetOn_DV0.0.0.f0214d0613 | TBD | Becker | Spec 尚未確定 iOS: 目前不能作動 20250610 APP --API : /v2/DevSend (UploadLog)--> 雲 --> AP fw : Log Sent to ?? ( Site )

## VLAN test
原始構圖
DUT:
| 5 | 1 | 2 | 3 | 4
|  | vlan 100 |  |  |  | ssid#1 with untag vlan 100 ))) | ((( phone#1
|  |  | vlan 200 |  |  | ssid#2 with untag vlan 200 ))) | ((( phone#2
| vlan 500 |  |  |  |  | ssid#3 with untag vlan 500 ))) | ((( phone#3
| untag 1 |  |  | untag 1 | untag 1 | ssid#4 ))) | ((( phone#4
| vlan 400 |  |  |  | vlan 400 | ssid#5 with untag vlan 400 ))) | ((( phone#5
Pre-test 版號:
DUT: 0.3.01
iOS App: 0.3.01
目前問題:
1. DHCPD reload issue 手法: 只做 test case 1, 建立>反向移除，反複做即可重現問題 環境: 只接E5 uplink (DHCP server for untag1), 其餘都不接
2. Config 有時候沒吃到 DUT (目前只知是random issue) 建立或反向移除VLAN設定都有發生過 懷疑 wifi 綁VLAN或移除VLAN後，若不等待，接著下一個設定步驟，剛好遇到wifi reload，有機率發生config 沒吃到的情況
3. Test Cast6 ，將DUT IP Address Setting DHCP改綁vlan400後，br0 死掉(ethner燈號不亮)，無法get DHCP server #400 > 重新開機後，就正常了
注意事項:
此分頁為 VLAN pre-test 用
並未完整測試2.4G/5G/6G，只專注vlan group通道流
每次App 設定完，Wi-Fi 會有 reload 時間，該時間尚化優化，故該測試的設定步驟都會等約 120 秒
16 SSID 未測
8 個VLAN grouop 未測
Test case 1: 測 E1E2+vlan 100
接法如右圖 | Up Link Internet | DHCP server #100
| ¦ | ¦
DUT: | 5 | 1 | 2 | 3 | 4
|  | vlan 100 | vlan 100 |  |  | ssid#1 with untag vlan 100 ))) | ((( phone#1 | <-vlan 100 stream
|  |  | PC#2 vlan100 PC#2 no vlan | PC#3 no vlan | PC#4 no vlan |  |  | <-vlan untag 1 stream
Steps: 1, Network Selection: 建立一個VLAN 100 2, Network Configuration: 將SSID#1 綁到 vlan100 (等120秒) 3, Online Device>Device List>Edit>Device Setting>VLAN Setting E1 綁 tag vlan 100 (… 等120秒) E2 綁 tag vlan 100 (… 等120秒) | note:>如果只做到第2步，不往下設定，brctl show 不會更新，必需Ethernet port 也綁 tag VLAN >>發生過 DHCPD reload issue (reboot 就好了，若不理它，需要擺很長一段時間，約30分以上，它有機會會自動恢復)
測試項目: | 結果: | 備註:
. PC#2(with vlan100) gets DHCP server#100 assigned IP. | PASS
. PC#2(no vlan-untag 1) gets DHCP server(untag 1), access Internet | PASS | E2 可以跑 tag 100 和 untag 1
. PC#3 and PC#4 get DHCP server(untag1), access Internet | PASS
. Phone#1 gets DHCP server#100 assigned IP. | PASS
.App 還原測試: 1, E1,移除 vlan 100 (… 等120秒) 2. E2 移除 vlan 100 (… 等120秒) 3, Network Selection>SSID#1 改成 ManagementVLAN(1)(等120秒) 4, Network Selection>Remove Vlan 100 5, 所有 port E1~E4 接PC 皆要能上網 6, phone#1 要能上網 | PASS | note: E1/E2 分次改，分次SAVE (如果同時改2port, 做一次SAVE，有發生過config 沒吃完整??) Chris: 目前先加上 "等120秒" 來測試 Chris: Wifi 變更 VLAN 目前沒有 動畫…，但實際操作也是要等待一下(不用到120秒)
Test case 2: 測 E1vlan 100 +E2vlan 200
接法如右圖 | Up Link Internet | DHCP server #100 | DHCP server #200
| ¦ | ¦ | ¦
DUT: | 5 | 1 | 2 | 3 | 4
|  | vlan 100 |  |  |  | ssid#1 with untag vlan 100 ))) | ((( phone#1 | <-vlan 100 stream
|  |  | vlan 200 |  |  | ssid#2 with untag vlan 200 ))) | ((( phone#2 | <-vlan 200 stream
|  |  |  | PC#3 | PC#4 |  |  | <-vlan untag 1 stream
Steps: 1, Network Selection: 再建立一個VLAN200 2, Network Selection: 再建立一個 SSID#2，並且綁VLAN200 (等120秒) 3, Online Device>Device List>Edit>Device Setting>VLAN Setting E2 改綁 tag vlan 200 (… 等120秒) | note:>如果只做到第2步，不往下設定，brctl show 不會更新，必需Ethernet port 也綁 tag VLAN >>重新砍掉，從test case1>test case 2 ，有發生過 config 吃不進來，重新開機就好了
測試項目: | 結果: | 備註:
. Phone#1 gets DHCP server#100 assigned IP. | PASS
. Phone#2 gets DHCP server#200 assigned IP. | PASS
. PC#3 and PC#4 get DHCP server(untag1), access Internet | PASS
. 把SSID#2，改綁到tag VLAN 100 (等120秒) Phone#2 gets DHCP server#100 assigned IP. | PASS | 測完改回VLAN200
Test case 3: 測 E1vlan 100+E2vlan 200+E5vlan500
接法如右圖 | Internet + DHCP server#500 | DHCP server #100 | DHCP server #200
| ¦ | ¦ | ¦
DUT: | 5 | 1 | 2 | 3 | 4
|  | vlan 100 |  |  |  | ssid#1 with untag vlan 100 ))) | ((( phone#1 | <-vlan 100 stream
|  |  | vlan 200 |  |  | ssid#2 with untag vlan 200 ))) | ((( phone#2 | <-vlan 200 stream
| vlan 500 |  |  |  |  | ssid#3 with untag vlan 500 ))) | ((( phone#3 | <-vlan 500 stream
|  |  |  | PC#3 | PC#4 |  |  | <-vlan untag 1 stream
Steps: 1, Network Selection: 再建立一個VLAN500 2, Network Selection: 再建立一個 SSID#3，並且綁VLAN500 (等120秒，DUT會斷ping，要等恢復ping後，再等一下，接著下面步驟) 3, Online Device>Device List>Edit>Device Setting>VLAN Setting E5 改綁 tag vlan 500 (… 等120秒) | note:>如果只做到第2步，不往下設定，brctl show 不會更新，必需Ethernet port 也綁 tag VLAN >步驟2，若不等待秒數，接著步驟3，有機率會遇到 config 沒吃到的情況 >有發生過 SSID#1 / SSID#3 起不來的狀況
測試項目: | 結果: | 備註:
. Phone#1 gets DHCP server#100 assigned IP. | PASS
. Phone#2 gets DHCP server#200 assigned IP. | PASS
. Phone#3 gets DHCP server#500 assigned IP. | PASS
. PC#3 and PC#4 get DHCP server(untag1), access Internet | PASS | E5 可以跑 tag 500 和 untag 1
Test case 4: 測 E1vlan 100+E2vlan 200+E5vlan500+wifi untag1
接法如右圖 | Internet + DHCP server#500 | DHCP server #100 | DHCP server #200
| ¦ | ¦ | ¦
DUT: | 5 | 1 | 2 | 3 | 4
|  | vlan 100 |  |  |  | ssid#1 with untag vlan 100 ))) | ((( phone#1 | <-vlan 100 stream
|  |  | vlan 200 |  |  | ssid#2 with untag vlan 200 ))) | ((( phone#2 | <-vlan 200 stream
| vlan 500 |  |  |  |  | ssid#3 with untag vlan 500 ))) | ((( phone#3 | <-vlan 500 stream
| untag 1 |  |  | untag 1 | untag 1 | ssid#4 ))) | ((( phone#4 | <-vlan untag 1 stream
|  |  |  | PC#3 | PC#4 |  |  | <-vlan untag 1 stream
Steps: 1, Network Selection: 再建立一個 SSID#4 (untag 1)
測試項目: | 結果: | 備註:
. Phone#1 gets DHCP server#100 assigned IP. | PASS
. Phone#2 gets DHCP server#200 assigned IP. | PASS
. Phone#3 gets DHCP server#500 assigned IP. | PASS
. Phone#4 can access the Internet. | PASS
. PC#3 and PC#4 get DHCP server(untag1), access Internet | PASS | E5 可以跑 tag 500 和 untag 1
Test case 5: 測 E1vlan 100+E2vlan 200+E5vlan500+wifi untag1+E4vlan400
接法如右圖 | Internet + DHCP #500 + DHCP #400 | DHCP server #100 | DHCP server #200
| ¦ | ¦ | ¦
DUT: | 5 | 1 | 2 | 3 | 4
|  | vlan 100 |  |  |  | ssid#1 with untag vlan 100 ))) | ((( phone#1 | <-vlan 100 stream
|  |  | vlan 200 |  |  | ssid#2 with untag vlan 200 ))) | ((( phone#2 | <-vlan 200 stream
| vlan 500 |  |  |  |  | ssid#3 with untag vlan 500 ))) | ((( phone#3 | <-vlan 500 stream
| untag 1 |  |  | untag 1 | untag 1 | ssid#4 ))) | ((( phone#4 | <-vlan untag 1 stream
| vlan 400 |  |  |  | vlan 400 | ssid#5 with untag vlan 400 ))) | ((( phone#5 | <-vlan 400 stream
|  |  |  | PC#3 | PC#4 vlan400 PC#4 no vlan
Steps: 1, Network Selection: 再建立一個VLAN400 2, Network Selection: 再建立一個 SSID#5，並且綁VLAN400(等120秒) 3, Online Device>Device List>Edit>Device Setting>VLAN Setting E5 加綁 tag vlan 400 (… 等120秒) E5: 共三個 VLAN 500+VLAN400+預設的untag1 4,E4 改綁 tag vlan 400 (… 等120秒) | >>發生過 DHCPD reload issue，已寄log 給 TI
測試項目: | 結果: | 備註:
. Phone#1 gets DHCP server#100 assigned IP. | PASS
. Phone#2 gets DHCP server#200 assigned IP. | PASS
. Phone#3 gets DHCP server#500 assigned IP. | PASS
. Phone#4 can access the Internet. | PASS
. Phone#5 gets DHCP server#400 assigned IP. | PASS
. PC#3 gets DHCP server(untag1), access Internet | PASS
. PC#4(no vlan-untag1 ) get DHCP server(untag1), access Internet | PASS
. PC#4(with vlan400) get DHCP server#400, access Internet | PASS
Test case 6: 測 E1vlan 100+E2vlan 200+E5vlan500+wifi untag1+E4vlan400>把DUT IP address綁VLAN400
Based on Test case 5 Steps: 1, Online Device>Device List>select one device>Device Status>Edit>IP Address Setting 2, 將ManagementVLAN(1) 改成 VLAN400 3, DUT IP 應該獲得 DHCP server #400 (此test case 有點疑慮，確定要讓 user 改 IP Address Setting + VLAN tagged 嗎?) |  | 20250710 Chris: v0.3.01, case5>case6, 步驟2之後，br0 死掉(ethner燈號不亮)，無法get DHCP server #400 > 重新開機後，就正常了 可100%複製，已寄log, config 給TI

## Scenario Test
Scenario #1 | In one site, AP can apply with different Network Settings.(SSID)
Description: | 一個site裡，有不同AP，每台AP 可以有不同設定 如: AP1 with SSID#1~#8 AP2 with SSID#1~4 AP3 with SSID#1~2
Environment: | Internet --- Router/Switch --- AP#1 +-- AP#2 +-- AP#3
Steps:
Expected Result: | 確保STA 可以連一所有AP的SSID
Scenario #2 | AP1 and AP3 switch the Network Settings.(SSID)
Description: | 一個site裡，有不同AP，每台AP 可以有不同設定，並且可以交換 如: AP1 with SSID#1~#8，AP2 with SSID#1~4，AP3 with SSID#1~2 將AP1 ，AP3 設定交換 變成如下: AP1 with SSID#1~2 AP2 with SSID#1~4 AP3 with SSID#1~8
Environment: | Internet --- Router/Switch --- AP#1 +-- AP#2 +-- AP#3
Steps:
Expected Result: | 確保STA 可以連一所有AP的SSID
Scenario #3 | One site with the maxium AP number = 10
Description: | 一個site裡，加上10台 將AP1 ，AP3 設定交換 變成如下: AP1 with SSID#1~2 AP2 with SSID#1~4 AP3 with SSID#1~8
Environment: | Internet --- Router/Switch --- AP#1 +-- AP#2 +-- AP#3
Steps:
Expected Result: | 確保STA 可以連一所有AP的SSID